## owssvr_latest
ID | Title | FirstAnswer | SecondAnswer | ThirdAnswer | FourthAnswer | Correct
2 | An Agile Developer is responsible for writing what level of documentation? | None, Agile doesn't require documentation | As much as he/she can write with as much detail as possible | Minimally sufficient, just enough to add value to the project | The same documentation as required by the Waterfall process | Minimally sufficient, just enough to add value to the project
3 | Which of the following is a valid Scrum Rule? | The Product Owner has until the 3rd day of the Sprint to add/delete user stories from the Sprint. | If the Team determines that it can address more Product Backlog during the Sprint than it selected during the Sprint planning meeting, it can select and add new items from the product backlog after discussions with the Product Owner. | The team can change the duration of each Sprint to match the workload | No one can provide advice, instructions, commentary, or direction to the Team during the Sprint. The Team is utterly self-managing. | If the Team determines that it can address more Product Backlog during the Sprint than it selected during the Sprint planning meeting, it can select and add new items from the product backlog after discussions with the Product Owner.
4 | Which statement below is true of Scrum? | User Stories are estimated in story points, while tasks are estimated in hours. | Both User Stories and tasks are estimated in hours. | User Stories are estimated in hours, while tasks are estimated in story points. | There is no estimation process for user stories or tasks. | User Stories are estimated in story points, while tasks are estimated in hours.
5 | The Agile Manifesto values which of the following statements? | Processes and Tools | Following a Plan | Working Software | Contract Negotiation | Working Software
6 | Agile teams are very predictable, based upon what? | The number of stores accepted by the Product Owner | How often team members attend the daily standup meeting | Their Velocity | Team Size | Their Velocity
7 | The INVEST model is used in what activity? | Grooming the Product Backlog | Prioritizing User Stories | Sizing User Stories | Writing User Stories | Writing User Stories
8 | During what Scrum ceremony does the team inspect and adapt themselves? | The Daily Standup | The Retrospective | The Review/Demo | The Sprint Planning Meeting | The Retrospective
9 | What description best describes an Agile team who has reached Level 4 transformation? | The team is actively engaged with an Agile Coach. | The team has been disbanded and is no longer using Agile. | The team is self sufficient and sustaining. | The team has a Product Owner and a ScrumMaster. | The team is self sufficient and sustaining.
10 | Which user story is an example of a Spike Story? | As a claims processor, I want the work in my queue sorted by due date, so that I can work on the oldest items first. | As a Scrum team, we need to conduct an analysis as to whether we buy or build a product, so that we can provide cost comparisons to the Product Owner. | As a Doctor, I want a fee schedule, so that I will be able to project my costs. | As an Ipad user, I want the ability to access my work files, so that I can continue to work if my pc crashes. | As a Scrum team, we need to conduct an analysis as to whether we buy or build a product, so that we can provide cost comparisons to the Product Owner.
11 | Which statement best describes the role of the Scrummaster? | Through my command and control style, I make decisions for my teams. | I sign up for my tasks and provide estimates for them. | I am a servant leader whose job is to remove roadblocks for my team. | I own the Product Backlog and priortize all user stories. | I am a servant leader whose job is to remove roadblocks for my team.
12 | Which best describes the attributes of a well written user story? | Who, what and when | Who, what and why | What, why and when | Who, why and when | Who, what and why
13 | Sprint Zero is: | The last Sprint executed before deploying to Production | A list of actvities that should be completed before the first Sprint | A Scrum Ceremony that occurs after every Retrospective | When the team demonstrates working software to the Product Owner | A list of actvities that should be completed before the first Sprint
14 | What is the recommended size for an Agile Team? | 7 +/- 2 Members | It depends on the project | There is no recommended size | 12 or less members | 7 +/- 2 Members
15 | In Scrum, who sets the direction for what the team works on? | The entire Team | The Scrummaster | The Agile Coach | The Product Owner | The Product Owner
16 | What is the expected deliverable at the end of every Sprint? | A potentially shippable product increment | At least 75% of Accepted User Stories | A Sprint Burndown Chart | Code that needs to be tested | A potentially shippable product increment
17 | What is best way to communicate with team members who are located outside of your office during a sprint planning meeting? | Conference call. | Chat window. | Video conference. | Email. | Video conference.
18 | User stories feature which of the following components? | Role, Function, Benefit | Reason, Functionality, Benefit | Risk, Functionality, Benefit | Risk, Feature, Business Reason | Role, Function, Benefit
19 | What is a Product Roadmap? | A list of reports and screens. | A view of release candidates. | Instructions for deployment. | A backlog Prioritization scheme. | A view of release candidates.
20 | What is a coding methodology that is sometimes confused with Agile? | Continuous integration | Cowboy coding | Automated unit testing | Test-driven development | Cowboy coding
21 | In an Agile project, stakeholder engagement management is defined as | The time after the product is launched when the stakeholders actually use the product | Establishing and maintaining mechanisms that ensure all current and future parties are participating in the life cycle of the project. | The individual or individuals that manage the Scrum team and sets direction for each sprint. | The group or individuals that are developing the code for each sprint | Establishing and maintaining mechanisms that ensure all current and future parties are participating in the life cycle of the project.
22 | With respect to a sprint, what does velocity measure? | How many sprints a team can do in a release | How much time it will take to complete a sprint | What day of the week a sprint will complete | The amount of work that a team can accomplish in a given sprint | The amount of work that a team can accomplish in a given sprint
23 | What is the difference between a release and iteration? | A release consists of many iterations | An iteration contains many releases | They are the same | They are mutually exclusive | A release consists of many iterations
24 | Which of the following is an example of high - bandwidth communication? | A face-to-face meeting | An email communication | A video conference | A live chat using audio facility | A face-to-face meeting
25 | The amount of time it takes for a feature to move from inception to completion is known as: | Cycle Time | Burn Rate | Velocity | Productivity | Cycle Time
26 | In Scrum methodology, the concept of timeboxing helps to avoid: | Student Syndrome | Halo effect | Murphy's law | Parkinson's law | Parkinson's law
27 | Which of the following best represents scrum principles? | Plan, Do, Check, Act | Transparency, Introspection, Adaptation | Communication, Coordination, Cooperation | Transparency, Inspection, Adaptation | Transparency, Inspection, Adaptation
28 | Who is responsible to fix an identified defect? | The Programmer who coded the defect | The Coach | The Team | The Product Owner | The Team
29 | What estimation technique is used to do estimation faster? | Planning Poker | Affinity Estimation | Wideband Delphi | Bottom up Estimation | Affinity Estimation
30 | Agile Methods are more amenable to an environment that is: | Uncertain and People-Oriented | Uncertain and Process-Oriented | Certain and People-Oriented | Certain and Process-Oriented | Uncertain and People-Oriented
31 | The Agile Manifesto was authored by the founding members of: | Scrum Alliance | Agile Project Leadership Network | Association of Agile Practitioners | Agile Alliance | Agile Alliance
32 | The Definition of Done is developed by whom? | The Development Team | The Product Owner | The Scrum Master | The Scrum Team | The Scrum Team
33 | What are the 3 levels of planning used by agile teams? | Strategy, Release, Close | Release, Iteration, Daily | Planning, Execution, Control | Initiation, Roadmap, Iteration | Release, Iteration, Daily
34 | What is the normal time estimate for a research story? | 2 Days | 1 Day | 4 Hours | 16 Hours | 1 Day
35 | Which information radiator is MOST useful in aligning the team's effort in right direction? | Build Status Indicator | Iteration Burndown Chart | Product BAcklog Display | Project Priority Chart | Iteration Burndown Chart
36 | Which of the following metrics can be standardized across agile teams? | Release Burndown | Cycle Times | Customer Support | Customer Satisfaction | Customer Satisfaction
37 | Which of the following is used to detect problems within a process? | Sprint | Health Check | Burndown Chart | Detailed Documentation | Health Check
38 | What do a task boards NOT show? | Stories | Tasks in Progress | Story Points | Total Iterations | Total Iterations
39 | Which of the following is an important function for an agile leader to implement in a team? | Scheduling | Planning | Adapting | Tasking | Adapting
40 | Which of the following is not an attribute of a user story? | Independent | Dependent | Small | Negotiable | Dependent
41 | Which of the following is not a scrum Value? | Focus | Openness | Respect | Friendship | Friendship
42 | Which of the following is not an agile estimation model? | Ideal Days | Narrowband Delphi | T Shirt Size | Story Points | Narrowband Delphi
43 | Which of the following is not an agile Myth? | No documentation needed in agile projects | Agile does not work with CMMi | Agile will not solves all the project management problems | There is no role for managers in agile | Agile will not solves all the project management problems
44 | Which of the following is not the characterstic of SCRUM? | Cross-Functional | Distributed | Co-located | Committed | Distributed
45 | What are the benefits of Agile Scrum software development? (Choose as many that apply) | a) Lower overall development costs | b) Makes code more manageable | c) Provides safety harness for future code enhancements | d) Toll-gates are in place with defined deliverables ensuring a full audit train and accountability. | A B C
46 | A scrum master is a “servant leader” what qualities does this person need to possess in order to be successful in the role? | Good listening skills | Ability to build community | Collaboration skills | Ability to instill trust with the team | All are correct
47 | How long are iterations? | Ideally this is 2 weeks | Ideally this is4 weeks | Ideally this is 6 weeks | Varies
48 | The role of the scrum master is to: | Manage the agile team, drive sprints and ensure timelines are met. | Make critical decisions on development issues | Help the team be accountable to themselves in doing so establishing the agile community | Responsible for helping the team make external commitments | Help the team be accountable to themselves in doing so establishing the agile community
49 | The three pilars of scrum are? | Transparency, Communication, Adaptation | Inspection, Adaptation, Evolution | Adaptation, Inspection, Communication | Transparency, Inspection, Adaptation | Transparency, Inspection, Adaptation
50 | The length of the daily scrum meeting should be | As long as is needed to get through the issues | 15 minutes | 20 Minutes | 30 Minutes | 15 minutes
51 | The role of the scrum master is to resolve impediments. Example of such impediments would be; (select all that apply) | I need help debugging a problem with ……. | I still have not got the software I ordered a month ago | The department VP has asked me to work on something else “for a day or two” | I canted get the infrastructure team to give me any time and I need to meeting with them. | All Apply
52 | We put Risks into backlog to: | To avoid having to keep a sperate risk list | Keep team focused on risks | Ensure that they get worked on in early iteration | Prevent team from forgetting about them | Ensure that they get worked on in early iteration
53 | What are the artifacts resulting from the sprint planning meetings? | Detailed project plan including the sprint sessions | The Sprint goals | A completed Sprint backlog | A completed Sprint backlog | The Sprint goals and A completed Sprint backlog
54 | The core scrum team should consist of the following roles. (choose all that apply) | Product Owner | Development Team | Scrum Master | Quality Assurance | Product Owner, Dev Team, Scrum Master
55 | Which of the following role is not part of Scrum | Scrum Master | Product Owner | Team | Person | Person
56 | What a Scrum iteration is called as | Stage | Sprint | Cycle | Phase | Sprint
57 | Involving the team in Planning and estimating and providing early feedback on delivery velocity is BEST used to mitigate what kind of risk? | Schedule flaws | Requirements creep | Employee turnover | Poor Productivity | Schedule flaws
58 | Can a Scrum Master and Product owner be same individual | True | False |  |  | False
59 | Which of the following is the best approach to estimation? | Opintions of experts | Anology | Disaggrigation | All apply | All Apply
60 | In Scrum,team activity is monitored and cordinated at what frequency | Hourly basis | Daily basis | Weekly basis | Monthly basis | Daily basis
61 | In Scrum,Product owner articulates product vision and then it evolves in to refined and priortized list of features known as | Phase Log | Product Backlog | Sprint Backlog | Feature Log | Product Backlog
62 | The following are true | At the end of each sprint and sprint review meeting is held. This meeting is intentionally kept informal and should be a natural result of the sprints. | The product backlog is a prioritized feature list, containing short description of all the functionally desired in a product. It typical comprises of features, bugs, technical work and knowledge acquisition. | A Scrum team does not include any of the traditional software engineering roles such as programmer, designer, tester, or architect | Daily Scrum meetings must happen daily and cannot be reduced to 2-3 times a week. | Answer 1 - 2 -3 are correct
63 | Scrum eliminates many of tasks required by lead because team becomes Self organized | True | False |  |  | True
64 | Which of the following is the best attribute for user stories to have? | Dependent | Independent | UnNegotiable | Large | Independent
65 | The following are true about the product owner role | The product Owner is a lead user of the system or an SME with a strong understanding of the system users and has the vision on the product and the ability to communicate it successfully to the agile team. | the Product Owner determines the number of sprints and determines the content of each sprint. | The product owner is responcible for leading the Scrum Meetings | The product owner is the same role as the ScrumMaster | The product Owner is a lead user of the system or an SME with a strong understanding of the system users and has the vision on the product and the ability to communicate it successfully to the agile team.
66 | During which phase of the scrum process should the team spend time breaking user stories into tasks? | Daily Standup | Release Planning | Sprint Planning | Story Sizing | Sprint Planning
67 | Which of the following responsibility does not belongs to Scrum Master | Prioritize Product Backlog | Removing impediments | Assigning tasks to team members | Remind team about the process | Assigning tasks to team members
68 | Which of the following best describes the meaning of timeboxed Sprint | There is a recommended amount of time for the Sprint | There is a predefined time limit for the Sprint | The time limit for Sprint must be reviewed daily | The time limit for Sprint must be extended | There is a predefined time limit for the Sprint
69 | How does a team know when a backlog item is done | Scrum Master announces the end | Testing of backlog is completed | It meets the team and product owner's negotiated definition of done | Sprint is over | It meets the team and product owner's negotiated definition of done
70 | Scrum is an agile process that allows | Focus on delivering highest buiness value in shortest time | The business to set priorities and the IT teams to self manage to dermine the best way to deliver the highest priority features. | The business to present minimal requirements and expect the agile team to adapt quickly to thier ever changing wims | for a comprehensive set of documentation and planning to take place to ensure what is being delivered is what the business asked for. | Answer 1 and 2
71 | Of the following choices, what is the key reason to adopt an agile process like Scrum | To be updated on latest process | To hold developers responsible for defect | To be better able to respond to changing requirements | To complete the project in fastest possible time | To be better able to respond to changing requirements
72 | A Daily Scrum is not | A problem solving session | A meeting in which team members make commitments to each other and to the scrum master | a good way for the scrum master to track the team | a 15 min session | A problem solving session
73 | In what order the product backlog be kept | Alphabetical | Chronological | Complexity | Priority | Priority
74 | A Product Backlog is not | A roadmap for long term product development | Requirements for a system in a prioritized list of backlog items | Managed by the product owner | Created during the sprint planning session | A roadmap for long term product development
75 | Who ultimately decides when the team has enough work for the Sprint | Scrum Master | Product Owner | The team | Scrum Master,The team and Product Owner vote to decide | The team
76 | Who can be invited to Sprint review meeting | Scrum Master and Team only | Scrum Master,Team and Product Owner only | Scrum Master and Product Owner only | Scrum Master,Team ,Product Owner and any one who is interested
77 | The following ensure the success of a Daily Scrum | The meeting starts precisely on time. | All are welcome, but normally only the core roles speak | The meeting length is set to 15 minutes | The meeting should happen at the same location and same time every day | all are true
78 | What happens when a backlog item fails to meet the negotiated definition of done at the end of Sprint | Team is always given extra time of 24 hours in such cases | Incomplete backlog item is placed back in backlog and repriortized by Product owner | Incomplete backlog item automatically gets included in next Sprint |  | Incomplete backlog item is placed back in backlog and repriortized by Product owner
79 | What is the primary purpose of Sprint burndown chart | To show, at a glance how many hours have been spent till date | To show, at a glance who is lagging behind in completing their tasks | To show, at a glance amount of work remaining in a Sprint |  | To show, at a glance amount of work remaining in a Sprint
80 | Retrospectives are… | meetings held once per Release to review the release efforts and identify opportunities for improvement to the team's processes. | meetings held at the end of each Iteration to review the iteration efforts and identify opportunities for improvement to the team's processes. | meetings held at the end of each Iteration to review the iteration efforts and identify strengths and weakness in the team's processes; reinforce the strengths, and agree on action items that will address the weaknesses. | weekly meetings to discuss issues and concerns regarding the User Stories in the Backlog. | meetings held at the end of each Iteration to review the iteration efforts and identify strengths and weakness in the team's processes; reinforce the strengths, and agree on action items that will address the weaknesses.
81 | Agile Sprints are… | a series of regularly-scheduled development cycles which progress from Requirements Analysis through Design, Development, and Testing activites in a sequential manner within the Sprint duration. | a series of standard-length time periods in which the Scrum Team plans and delivers specific work for the review and approval of the Product Owner. | short, daily meetings where the team's progress and any blockers are discussed. | time-boxed efforts intended to deliver code to the Quality Assurance group for final testing. | a series of standard-length time periods in which the Scrum Team plans and delivers specific work for the review and approval of the Product Owner.
82 | Jerry, a software engineer on an Agile Scrum Team needs clarification of an Acceptance Criterion and he cannot proceed with his work until it is resolved. The team has already held their Scrum Meeting for the day. He should… | send an e-mail to the Scrum Master requesting that a meeting be set up between Jerry and the Product Owner to discuss Jerry's questions. | wait until the next day's Scrum Meeting to raise his questions. | send an email to the best team member to answer his question, whether an Analyst or the Product Owner. | phone, IM, or talk directly to the User Story Owner to get the necessary clarification as quickly as possible so that he can return to his assigned work. | phone, IM, or talk directly to the User Story Owner to get the necessary clarification as quickly as possible so that he can return to his assigned work.
83 | An Agile Scrum Team consists of… | the developers who are responsible for writing the code. | a Product Owner, Scrum Master, Software Engineers, Quality Assurance Analysts, Systems Analysts, and Business Analysts tasked with the release of a product. | the Product Owner, Scrum Master, and the remaining Scrum Team members who contribute to the final product to be delivered. Specific roles are less important on a Scrum Team. | a loosely-matrixed software development team assigned to work on an Agile project part-time. | the Product Owner, Scrum Master, and the remaining Scrum Team members who contribute to the final product to be delivered. Specific roles are less important on a Scrum Team.
84 | Committing to a Sprint means that… | the team is in agreement on the start and end dates of the Sprint. | the User Stories are clear and can be worked on. | the User Stories in the Sprint have been groomed, everyone understands the Acceptance Criteria, tasks have been identified, and everyone on the team is committing to complete the User Stories within the Sprint timeframe. | the software engineers have committed to completing all of the coding within the Sprint. | the User Stories in the Sprint have been groomed, everyone understands the Acceptance Criteria, tasks have been identified, and everyone on the team is committing to complete the User Stories within the Sprint timeframe.
85 | Common Scrum Methodology Meetings include… | Backlog Grooming, Daily Standup, Sprint Planning, Sprint Retrospective, Sprint Demo, Weekly Status, Project Plan Review, Release Planning, Requirements Review | Backlog Grooming, Daily Standup, Sprint Planning, Sprint Retrospective, Sprint Demo, Release Planning | Daily Standup, Sprint Planning, Sprint Retrospective, Sprint Demo, Project Plan Review, Release Planning, Requirements Review | Business Funding Review, Backlog Grooming, Daily Standup, Sprint Planning, Sprint Retrospective, Sprint Demo, Weekly Status, Project Plan Review, Release Planning, Requirements Review, Performance Review | Backlog Grooming, Daily Standup, Sprint Planning, Sprint Retrospective, Sprint Demo, Release Planning
86 | The primary questions to be answered in a Daily Standup are… | When will you complete your assigned User Stories? What is the status of your documentation? How many hours have you spent on the project to-date? | What is working well? What is not working well? What can we do to improve the things that are not working well? | What did you do yesterday? What are you going to do today? What is getting in your way? | Does everyone understand all of the User Stories? Are all of the tasks estimated correctly? Does everyone commit to completing the User Stories in the Sprint? | What did you do yesterday? What are you going to do today? What is getting in your way?
87 | The INVEST acronym stands for… | Important, Negotiable, Valuable, Estimable, Small, Testable | Independent, Negotiable, Valuable, Estimable, Small, Testable | Important, Negotiable, Valuable, Effective, Small, Testable | Independent, Negotiable, Valuable, Estimable, Small, Trackable | Independent, Negotiable, Valuable, Estimable, Small, Testable
88 | What is the primary measure of progress in agile software projects? | Function points | Working software | The burn down chart | The information radiator | Working software
89 | Which of the following is not part of 3 Cs of a user story? | Card | Confirmation | Conversation | Conceptualization | Conceptualization
90 | If a team member is not performing up to team expectations, who should address this? | The scrum master | The team | The customer | The person or the group recruited the team member | The team
91 | Test driven development is characterized by which of the following? | Test, code, refactor, deliver | Code, test, refactor, deliver | Code, refactor, test, deliver | Test, code, deliver, refactor | Test, code, refactor, deliver
92 | A small unit which adds value to the customer is known as: | A story point | A minimal marketable feature | A function point | a use case | A minimal marketable feature
93 | In agile terminology, the epic is also known as: | A capability | A node | An iteration span | A root feature | A capability
94 | Which of the following team size is allowed for a scrum team? | 3 | 8 | 10 | 12 | 8
95 | During planning poker, the team provides estimates in: | Days | Hours | Story points | Dollars | Story points
96 | Actual time and ideal time differ bacause of: | Interruptions | Miscalculations | Respond to change | The coefficient of team friction | Interruptions
97 | The team has installed a new version control package to help with daily builds. This is an example of: | Technical debt | Agile tooling | Integrated technology | Agile configuration management | Agile tooling
98 | Which acronym below describes the product backlog? | DEEP | INVEST | SURE | GROOM | DEEP
99 | The opposite of an information radiator is: | An information broker | An information vaccum | An information consolidator | An information refrigerator | An information refrigerator
100 | All other things being equal, which estimating technique is the fastest? | Planning poker | Affinity estimating | Wideband delphi | Scatter | Affinity estimating
101 | What is the ordering of the below items from biggest to smallest in terms of the size? | Epic, theme, story | Theme, epic, story | Story, theme, epic | These are not related at all | Epic, theme, story
102 | What is the most suitable contract type for an agile project? | Fixed Price | Time and material | Fixed time | Fixed cost | Time and material
103 | Which of the following is used to ensure collaboration in a fun team environment? | Daily stand up | Planning poker | Innovation games | Retrospective | Innovation games
104 | During a 2 week sprint, a scrum team delivered 3 stories estimated at 5 story point each and 2 stories estimated at 3 story points each. What is the velocity of this team? | 21 | 10.5 | 30 | 12 | 21
105 | What is a maximum allowed time in hours for a task in sprint work? | 9 | 12 | 16 | 24 | 16
106 | Which of the following factors you should keep in mind while prioritizing the user stories? | Value, cost, risk | Value, quality, cost | Time, cost, risk | Time, cost, quality | Value, cost, risk
107 | Tasks such as establishing environments, finalizing contracts, high level estimation and activities related to implementation readiness are usually part of: | Sprint -n | Sprint 0 | Sprint 1 | Sprint H | Sprint 0
108 | There are less important stories that team can set aside if they need more time and they are called as: | Silver stories | Gold stories | Zero stories | Set aside stories | Silver stories
109 | DRY is the acronym for: | Don't repeat yourself | Don't review yourself | Do review yourself | Do retrospect yourself | Don't repeat yourself
110 | Which of the following resembles change in code but no change in behaviour? | TDD | Recoding | Refactoring | Spike solution | Refactoring
111 | Which of the following allows programmer to be confident that their code does what they think it should? | Customer test | TDD | Refactoring | Test last | TDD
112 | Those who have committed to the project and responsible for the outcome of the agile project is called? | Hen | Chicken | Pig | Goat | Pig
113 | Which of the following statement is correct for a scrum team? | Team having velocity as 20 is efficient than Team having velocity as 30 | Team having velocity as 30 than Team having velocity as 20 | Team has velocity as 50 than Team having velocity as 30 | There is no relation between efficiency and velocity for the scrum teams | There is no relation between efficiency and velocity for the scrum teams
114 | Who conducts daily scrum meeting? | Scrum master | Product owner | The scrum team | Project manager | The scrum team
115 | Which of the following is a product vision game? | Product table | Product chair | Product box | Product cot | Product box
116 | Which one of the following is a special communication, which is possible in agile project teams? | Osmatic communication | Group communication | Team communication | General communication | Osmatic communication
117 | When a defect is found by the customer after the build is handed over to the customer, is known as? | Known issue | Onshore defect | Escaped defect | Open secret | Escaped defect
118 | Suppose a story was estimated to be 5 story points, the team acknowledges that they should have estimated it at 9 story points. This story contributes how many points to the velocity calculations? | 9 | 14 | 5 | 4 | 5
119 | Which of the following is the major purpose of the kanban board? | Not started work tracking | In progress work tracking | Completed work tracking | WIP limits tracking | WIP limits tracking
120 | An epic that comprises multiple shorter stories is called as: | Complex story | Confused story | Compound story | Complicate story | Compound story
121 | Which of the following use controlled experiment? | Customer test | TDD | Refactoring | Spike solution | Spike solution
122 | Agile projects are best estimated by: | Bottom up | Top down | Analogous | Left to right | Top down
123 | Chickens and pigs are the characters in: | DSDM | RUP | Scrum | Kanban | Scrum
124 | Which of the following sport is related with the term scrum? | Hockey | Cricket | Rugby | Foot ball | Rugby
125 | Which of the following is a role in scrum? | Delivery Manager | Project Manager | Scrum Manager | Scrum Master | Scrum Master
126 | Which of the following is an example of wideband delphi technique? | Coffee mug estimate | T shirt estimate | Affinity estimate | Planning poker | Planning poker
127 | Which of the following is useful for risk management in agile projects? | Burndown tracker | Burnrate tracker | Burnup tracker | Impediment Tracker | Impediment Tracker
128 | The use of stories in agile promotes which agile manifesto principle most? | Individuals and interactions over processes and tools | Completed functionality over comprehensive documentation | Customer collaboration over contract negotiation | Responding to change over following a plan | Customer collaboration over contract negotiation
129 | A cross functional team means: | Having both developers and QA on the team | Having team members that can do lots of things | Including the scrum master and product owner as part of the team | Making sure that the team has whatever skills are necessary to do the job | Making sure that the team has whatever skills are necessary to do the job
130 | The agile manifesto value “Responding to change over following a plan” best means: | Agile projects encourage change | Planning has little value in agile | The product owner can change their mind at any time | Change has little impact on agile projects | The product owner can change their mind at any time
131 | What is the best reason why scrum practices can make distributed teams more effective? | Team members in different time zones can work on the same thing without getting in each other’s way | Scrum encourages frequent communication between the team and the business | It is easier to coordinate a small distributed team than a large one | You can use the best resources available regardless of their location | Scrum encourages frequent communication between the team and the business
132 | Who can add items to the product backlog? | Business analysts | Team members | The product owner | Anyone | Anyone
133 | Items can be added to the product backlog: | any time | only prior to the start of a sprint | if funding is approved | if the team agrees to it | any time
134 | Size estimating is useful because: | Everyone can understand story points | You can use planning poker to quickly estimate things | It is independent of who does the work | You do not have to know much about the item to estimate it | It is independent of who does the work
135 | Scrum is best described as a: | Process | methodology | Framework | Practice | Framework
136 | a scrum master duties are most closely aligned with: | A manager | An architect | A coach | A consultant | A coach
137 | What of the following items istime-boxed in scrum? | A sprint activity | Estimating a story | A retrospective | Answering the 3 daily scrum questions | A retrospective
138 | Which characteristic is most important for a scrum master? | Strong knowledge of the product | Ability to understand everyone on the team | Strong knowledge of the scrum tools being used | Good facilitation skills | Good facilitation skills
139 | The scrum master has: | No authority | Authority over the team | Authority over the process | Authority over the product owner | Authority over the process
140 | If a team fails to delivery what was committed to in a sprint, the scrum master should ask: | the team commit to less points next time | a senior developer to start doing code reviews | the team to do more pair programming | the team what they can do different | the team what they can do different
141 | A retrospective should occur: | After every sprint | After every release | When the product owner requests | Whenever it is valuable | Whenever it is valuable
142 | If the team feels a member is not performing they should initially: | Tell the product owner | Tell his manager | Tell the scrum master | Tell him/her | Tell him/her
143 | When there is a conflict, who should be resolving? | The product owner | The agile coach | The team | The scrum master | The team
144 | Who is responsible to resolve the impediments? | Scrum master | Product owner | Project manager | Scrum team | Scrum team
145 | The CEO asks the Development Team to add a "very important" item to the current Sprint. What should the Development Team do? | Add the item to the current Sprint without any adjustments. | Add the item to the current Sprint and drop an item of equal size. | Add the item to the next Sprint. | Inform the Product Owner so he/she can work with the CEO. | Inform the Product Owner so he/she can work with the CEO.
146 | When is a Sprint over? | When all Product Backlog items meet their definition of done. | When the Product Owner says it is done. | When all the tasks are completed. | When the timebox expires. | When the timebox expires.
147 | What is the primary way a Scrum Master keeps a Development Team working at its highest level of productivity? | By facilitating Development Team decisions and removing impediments. | By ensuring the meetings start and end at the proper time. | By preventing changes to the Backlog once the Sprint begins. | By keeping high value features high in the Product Backlog. | By facilitating Development Team decisions and removing impediments.
148 | Who is required to attend the Daily Scrum? | The Development Team. | The Scrum team. | The Development Team and Scrum Master. | The Development Team and Product Owner. | The Development Team.
149 | Development Team membership should change: | Every Sprint to promote shared learning. | Never, because it reduces productivity. | As needed, while taking into account the short term reduction in productivity. | Just as it would on any development team, with no special allowance for changes in productivity. | As needed, while taking into account the short term reduction in productivity.
150 | Who is responsible for updating the work estimates during a Sprint? | The Development Team. | The Scrum Master. | The Product Owner. | The most junior member of the Team. | The Development Team.
151 | Why is the Daily Scrum held at the same time and same place? | The place can be named. | The consistency reduces complexity and overhead. | The Product Owner demands it | Rooms are hard to book and this lets it be booked in advance. | The consistency reduces complexity and overhead.
152 | When a Development Team determines that it has over-committed itself for a Sprint, who has to be present when reviewing and adjusting the Sprint work selected? | The Scrum Master, project manager and Development Team. | The Product Owner and Development Team. | The Product Owner and all stakeholders. | The Development Team. | The Product Owner and Development Team.
153 | The maximum length of the Sprint Review (its time box) is: | 2 hours | 4 hours for a monthly Sprint, proportionally less for shorter Sprints | As long as needed | 1 day | 4 hours for a monthly Sprint, proportionally less for shorter Sprints
154 | Which statement best describes Scrum? | A complete methodology that defines how to develop software. | A cookbook that defines best practices for software development | A framework within which complex products in complex environments are developed. | A defined and predictive process that conforms to the principles of Scientific Management. | A framework within which complex products in complex environments are developed.
155 | What does it mean to say that an event has a timebox? | The event must happen at a set time. | The event must happen by a given time. | The event must take at least a minimum amount of time | The event can take no more than a maximum amount of time. | The event can take no more than a maximum amount of time.
156 | The Product Backlog is ordered by: | Small items at the top to large items at the bottom. | Safer items at the top to riskier items at the bottom. | Least valuable items at the top to most valuable at the bottom. | Whatever is deemed most appropriate by the Product Owner. | Whatever is deemed most appropriate by the Product Owner.
157 | Which statement best describes a Product Owner's responsibility? | Optimizing the Return on Investment (ROI) and the Total Cost of Ownership (TCO) of the work the Development Team does. | Directing the Development Team. | Managing the project and ensuring that the work meets the commitments to the stakeholders. | Keeping stakeholders at bay. | Optimizing the Return on Investment (ROI) and the Total Cost of Ownership (TCO) of the work the Development Team does.
158 | Which statement best describes the Sprint Review? | It is a review of the team's activities during the Sprint. | It is when the Scrum Team and stakeholders inspect the outcome of the Sprint and figure out what to do in the upcoming Sprint. | It is a demo at the end of the Sprint for everyone in the organization to provide feedback on the work done. | It is used to congratulate the Development Team if it did what it committed to doing, or to punish the Development Team if it failed to meet its commitments. | It is when the Scrum Team and stakeholders inspect the outcome of the Sprint and figure out what to do in the upcoming Sprint.
159 | The reason the Scrum Master is at the Daily Scrum is: | To make sure everyone answers the three questions in order of seniority. | He or she does not have to be there; he or she only has to ensure the Development Team has a Daily Scrum. | To write down any changes to the Sprint Backlog, including adding new items, and tracking progress on the burndown. | So he or she knows what to report to management. | He or she does not have to be there; he or she only has to ensure the Development Team has a Daily Scrum.
160 | Who has the last say on the order of the Product Backlog? | The Stakeholders | The Development Team | The Scrum Master | The Product Owner | The Product Owner
161 | When many Development Teams are working on a single product, what best describes the definition of "done?" | Each Development Team defines and uses its own. The various differences are discussed and reconciled during the stabilization phase. | Each Development Team uses its own but must make it clear to all other Teams if there are differences. | All Development Teams must have a definition of "done" that when their work integrates results in a definition of "done" that is potentially releasable. | It depends. | All Development Teams must have a definition of "done" that when their work integrates results in a definition of "done" that is potentially releasable.
162 | The Development Team should have all the skills needed to: | Complete the project as estimated when the date and cost are committed to the Product Owner. | Do all of the development work, but not the types of testing that require specialized testing, tools, and environments. | Turn the Product Backlog it selects into an increment of potentially shippable product functionality. | To finish the sprint with in budget | Turn the Product Backlog it selects into an increment of potentially shippable product functionality.
163 | An agile team has estimated a user story with to have ten story points. Which of the following statement is true? | A ten-point story is half as big, complex and risky as a twenty point story | A ten-point story is half as big, complex and risky as a five point story | A ten-point story is twice as big, complex and risky as a twenty point story | A ten-point story is of same size as twenty point story | A ten-point story is half as big, complex and risky as a twenty point story
164 | You are a product owner and you are working on prioritizing the product backlog items. Which of the following is the best way to prioritize a product backlog? | Consider only risks | You are the product owner so whatever you want you do | Risk first and Value second | Value first and Risk second | Value first and Risk second
165 | For any Agile project, how the project schedule is prepared? | Using story points and put them in sequence to arrive at schedule | Using story points to estimate the total size of the project and using the team velocity to determine the time required to deliver the size | Using a WBS and microsoft project | Using planning poker estimate | Using story points to estimate the total size of the project and using the team velocity to determine the time required to deliver the size
166 | Which of the following statement best describes "Governance" in an Agile environment? | Controlling the Agile teams | Agile project progress tracking | Making decisions in an uncertain environment | Directing the output of an Agile team | Making decisions in an uncertain environment
167 | Select the correct option from the below that describes the "Servant Leadership" | The leader taking whatever tasks the team requests | The leader inspiring the team to take a "servant mentality" | The leader ensuring the team's highest priority needs are met | The scrum master arranges assistants to the team members | The leader ensuring the team's highest priority needs are met
168 | You are the project manager and your team intentionally decided to go with a technical solution. This solution may get into a risk of schedule slippage of current iteration. What is your most appropriate action/response as a PM? | Order the team not to follow with the solution that they decided | Ask some External Technical Experts to review the solution and provide their recommendations | Let the team go with the solution, allowing the team itself to manage the risk | Consult senior management for their support | Let the team go with the solution, allowing the team itself to manage the risk
169 | What is the primary intention of Daily stand-up meeting? | To check who is absent and may come late to work today | To check quickly for the team's leave plans in coming few days | Inspect and adapt work plans | Prioritize the work and assign to every team member | Inspect and adapt work plans
170 | Which of the following statement is the best description of the role of an Agile project leader? | Focusses on following processes | Focusses on tracking work progress | Focusses on updating management with the impedements | Focusses on delivering customer value | Focusses on delivering customer value
171 | Which of the following options best describes the role of a PMO in Agile project organization? | Maintains and checks the supply chain management | Keeps track of individual project execution | Provides insight to stakehlders of value delivered | Providing required resources to the Agile projects | Provides insight to stakehlders of value delivered
172 | How can be the risks related to schedule flaws mitigated? | By providing detailed user stories | By involving the team in planning and estimating | By having product owner working with the team | By getting senior management support | By involving the team in planning and estimating
173 | In Agile projects, what is the correct explanation for "Progressive Elaboration"? | This is the best approach to coach the agile teams | This is used to understand customer requirements better | It is the evolution of the project plan as more details are known (emerge) | It is the short form of team formation stages | It is the evolution of the project plan as more details are known (emerge)
174 | You are the project manager of an Agile project. One of your team members has committed a code change, which has caused a couple of unit tests to fail. What should be the next best step? | Rollback the change | Update customer about the failing tests as known bugs | Discuss with Product Owner on the next steps | Remove the story that causes the issues from the current sprint | Rollback the change
175 | Which of the following does not describe a potential effect of an undetected (escaped) defect in product design? | Loss of life | Loss of comfort | Loss of descritionary money | Loss of progress made in sunk costs | Loss of progress made in sunk costs
176 | In a large organization preparing to Adopt Agile, who should be designated as owner of retrospectives? | PMO (Project Management Office) | Project manager | Project leader | Scrum master | PMO (Project Management Office)
177 | What is the ideal duration for code integration in Agile projects? | At the end of every day | As soon as the developer completes his/her module | Every few hours | After unit testing is done | Every few hours
178 | Which of the following offers the most valuable product feedback? | Iteration Demo to Senior Management and other stakeholders | Release into market | Focus group | Sprint retrospective meeting | Release into market
179 | What is the process that kicks off an Agile release? | Stakeholder engagement meeting | Scrum planning meeting | Release retrospective meeting | Release planning meeting | Release planning meeting
180 | For Refactoring to be effective, which of the following are required? | Collective code ownership | Peer review for the code | Good coding standards | Good Tests | Good Tests
181 | Health checks are being used in Agile projects for what purpose? | To check the project progress | To act as MIS report | To put pressure on the team | To detect problems within a process | To detect problems within a process
182 | What is ROTI technique used to measure? | To measure the team velocity per iteration | To measure the left over items in the product backlog with respect to time | To measure the effectiveness of the retrospective meeting | To measure the customer involvement in the iteration planning | To measure the effectiveness of the retrospective meeting
183 | Which of following activity is not found in Scrum framework? | Weekly scrum/stand up | Sprint Planning | Sprint Review | Sprint Retrospective | Weekly scrum/stand up
184 | Scrum of scrums is knows as: | Alpha scrum | Beta scrum | Major scrum | Meta scrum | Meta scrum
185 | As part of daily standup meeting, which of the below question is not answered by team member? | What did you do yesterday? | What will you do today? | Are there any impediments in your way? | What will you learn today? | What will you learn today?
186 | Out of the following choices, what is the plausible approach, in case an issue is raised in daily stand up meeting? | Issues that are raised are taken offline and usually dealt with by the relevant sub-group immediately after the meeting | Issues are entered in issue tracker and escalated to Scrum master via email | Daily StandUp Meeting is extended by another 30 minutes to solve the issue | Team member is asked to go through the Scrum rules again and instructed to solve issue on his/her own. | Issues that are raised are taken offline and usually dealt with by the relevant sub-group immediately after the meeting
187 | What is the primary purpose of the sprint review? | To review the completed stories and look for opportunities to improve the product | To demo the system for upper management | To prove that the team worked hard during the sprint | To find out who failed to complete his or her tasks | To review the completed stories and look for opportunities to improve the product
188 | What are 3 Ws with respect to an user story? | Who, what, why | Who, when, why | Who, why, will | Why, whom, what | Who, what, why
189 | Out of the following choices, which one is not considered for spike story? | Research | bug debt | Process or engineering improvements | Innovation | Innovation
190 | Of the following choices, which best describes a Scrum Epic? | A scrum epic is a large user story | A scrum epic is a technically complex but directly implementable user story | A scrum epic is a user story having lowest priority | A scrum epic refers to collection of user stories which we discard from product backlog | A scrum epic is a large user story
191 | Who should control the second half of the daily scrum? | Scrum master | Product owner | Project manager | There is no second half as such in daily scrum | There is no second half as such in daily scrum
192 | What does Scrum advise a team do with the product backlog items it chooses to bring into the sprint | The team doesn't do anything with the product backlog items. | The team asks the Scrum Master to research the product backlog items and decide who should work on each one | The product owner assigns each product backlog item to the specialist best suited to carryout the work | The team should break each product backlog item into tasks and estimate each task interms of effort | The team should break each product backlog item into tasks and estimate each task interms of effort
193 | Which of the following is not part of the UHG agile core layers? | Formulating team | Adhering scrum practices | Following technical practices | FDD | FDD
194 | When a user story is finished? | When coding is done | When testing is done | When refactoring is done | When product owner accepted | When product owner accepted
195 | In practice during planning poker estimation, when a team member wanted to take a break, which card should be shown? | Tea cup | Coffee mug | Water glass | ? | Coffee mug
196 | In practice during planning poker estimation, when a team member do not know what to do about estimation, which card should be shown? | Coffee mug | ? | ! | % | ?
197 | In practice during planning poker estimation, when a team member think it takes a lot of time about estimation, which card should be shown? | ? | ! | * | Card having infinite symbol | Card having infinite symbol
198 | When is the product backlog ready? | Before the release planning meeting | Just before the sprint planning meeting | After the sprint 0 review | The Product backlog is never ready | Before the release planning meeting
199 | Out of the following choices, which item does not fall under technical debt? | Bad Design | Insufficient test coverage | Excessive manual testing | Immature Team member | Immature Team member
200 | A major theme in Scrum is “inspect and adapt.” Which of thefollowing best summarizes that theme? | Scrum insists on auditors who frequently inspect the work of the team and suggest ways to adapt the process in order to improve quality. | Scrum recommends that upper management inspect the burndown charts and notes from the dailyscrums to find ways in which the team should adapt their practices to be more productive. | Inspect and adapt refers to the scrummaster's role in inspecting the work and writing stories designed tohelp the team produce higher quality software | Scrum emphasizes taking a short step of development, inspecting both the resulting product and the efficacy of current practices, and then adapting the product goals and process practices. | Scrum emphasizes taking a short step of development, inspecting both the resulting product and theefficacy of current practices, and then adapting the product goals and process practices.
201 | Which of the following best describes a sprint? | A sprint is a condensed amount of time in which a development team works as many hours as they need to in order to finish the work assigned to them | A sprint is a fixed amount of time set aside for a team to run tests and fix any outstanding bugs right before the product ships | A sprint is a pre-specified period of time during which team members choose individual items from theproduct backlog to work on. as each item is completed, a new item is brought into the sprint | A sprint is a pre-specified amount of time in which the development team works at a sustainable pace tocomplete a chosen set of work | A sprint is a pre-specified amount of time in which the development team works at a sustainable pace tocomplete a chosen set of work
202 | Which of the following is NOT a responsibility of the product owner? | Assigning tasks to team members during thesprint | Inspecting work at sprint review | Keeping the product backlog up to date | Prioritizing the product backlog | Assigning tasks to team members during the sprint
203 | Who is authorized to suspend the sprint work? | Scrum master | Product owner | Project manager | Scrum team | Product owner
205 | In Scrum, the prioritized work to be done is referred to as: | product backlog | sprint retrospective | standup meetings | standup meetings | product backlog
206 | How frequent are Scrum project status meetings recommended to be held? | daily | weekly | monthy | mornings | Daily basis
207 | A Self Managed or Self Organized team is a team... | where each person works by themselves and passes work off to the next team member when deadlines are near. | that decides what to work on by picking the most interesting user stories. | is accountable for results and shares responsibilty for team effectiveness, value and ownership. | is responsible for planning and organizing their work assuming they know everything. | is accountable for results and shares responsibilty for team effectiveness, value and ownership.
208 | A Product Owner is responsible for the ROI of the project, which means that the Product Owner chooses to develop product functionality that solves critical business problems. The Prodcut Owner can increase the ROI by: | Frequently Culling and Sorting the priorities in the Product Backlog to reflect requirements with the highest business value. | Assinging highest value tasks to the person that can get the task done the quickest. | Calling for a release of functionality when the business benefit is less than the costs of implementation. | Asking the team which requirement will be easiest to complete in the shortest time. | Frequently Culling and Sorting the priorities in the Product Backlog to reflect requirements with the highest business value.
209 | In Scrum, the Retrospective is attended by: | The Team | The Product Owner | The Project Sponsor from a dependent project | The Finance Representative | The Team
210 | Who is supposed to give the sprint demo to the stakeholders? | Scrum master | Product owner | Project manager | There is no rule of thumb, any team memember can give the demo for their respective implemented stories or even can represent the entire team. | There is no rule of thumb, any team memember can give the demo for their respective implemented stories or even can represent the entire team.
211 | When a sprint ends? | When developer coding is complete | When a tester tests the stories | When PO accepts the completed stories | When the timebox is over | When the timebox is over
212 | What might happen when the end customer or product managers or product owner fail to agree on specification? | Communications setting | Specification breakdown | Feature breakdown | Cohesive breakdown | Specification breakdown
213 | A group of programmers were constantly loosing the focus which resulted in delay of their development activities. The management decided to send this group of programmers to an off-site location for a week to get a lot accompli | The Bus-length communication principle | The Cone of Silence strategy | The Expert in Earshot strategy | Outsourcing | The Cone of Silence strategy
214 | What should your Agile team do to mitigate to risks associated with intrinsic schedule flaw? | Re-evaluate the release plan at the end of each iteration | Re-evaluate the release plan at the end of the project | Execute tasks in parallel as much as possible | Increase the team members | Re-evaluate the release plan at the end of each iteration
215 | Identify the incorrect product feedback loop from the below options | Iteration demo | Release into market | Focus group | Daily Standup | Daily Standup
216 | A person from HR department can be invited to which of the following scrum ceremony? | Daily scrum | Sprint retrospective | Development team meeting | Release or project retrospective | Release or project retrospective
217 | Your senior management wants to see a code coverage metrics report in order to evauate whether your adoption of your Agile practices is culminating into better unit testing. How would you schedule this report generation? | I will ask Product Owner to prioritize it in the product backlog | As a regular task after every iteration | As a separate story | I will assign this task to one of the team members who have bandwidth | As a separate story
218 | Which retrospective is best to deal with cross organizational issues? | Iteration retrospective | Project/Release retrospective | Sprint retrospective | Daily retrospective | Project/Release retrospective
219 | When features are written so as to minimize the technical dependencies between, the product owner has the greatest amount of flexibility to do what with them? | Restrict | Deliver | Prioritize | Weigh | Prioritize
220 | Out of the following choices, Which describes best about Scrum Planning approach | Scrum planning is done only once | Scrum planning is non iterative | Scrum planning places emphasis on the plan | Scrum planning places emphasis on planning and is iterative | Scrum planning places emphasis on planning and is iterative
221 | A Persona used with in a user story can be thought of as: | A Person who will use the application infrequently | A Person who will influence early adopters of the application being developed | A person formally assigned as a user-acceptance tester | An imaginary representation of user role | An imaginary representation of user role
222 | What is the unit of measurement to measure the size of a user story? | Function Points | Velocity Points | Work break down points | Story Points | Story Points
223 | As an Agile project manager which of the following should you focus on first? | Tasks | Iteration goals | Team performance | Deliverables | Deliverables
224 | What is primary objective of a daily stand-up meeting? | It encourages peer-to-peer coordination and collaboration through information exchange | It increases the team politics | It gives good chance for Scrum master to know his team members well | Keep the stakeholders and product owner informed | It encourages peer-to-peer coordination and collaboration through information exchange
225 | In Agile project, what is the most appropriate time to produce a change report? | At the end of the project | At the end of each iteration | At the end of every daily stand up meeting | Whenever product owner wants the change report | At the end of each iteration
226 | Which of the following options is one of the 4 layers of an Agile enterprise framework? | Project execution | Project Management | User story mapping | Stakeholder management | Project Management
227 | Out of the following choices, Which best describes a Scrum Team: | Self-Organized and cross-functional | Self Learned and Functional | Self Managed and Non Functional | Self Lead and cross-functional | Self-Organized and cross-functional
228 | What is Abnormal Termination? | It refers to cancellation of Sprint by Product Owner | It refers to cancellation of Scrum Project by Scrum Master | It refers to cancellation of task by team member | It refers to cancellation of task by Scrum Master | It refers to cancellation of Sprint by Product Owner
229 | Which story points are valid? | 1,2,3,5,8.13 | 1,2,3,4,5,6 | 2,3,4,5,6,7 | 1,2,3,5,8,11 | 1,2,3,5,8.13
230 | How often should scrum meetings be held? | Once a week | Twice a week | Monthly | Daily | Daily
231 | The 3 core roles in the scrum process are? | Product Owner, Team, Scrum Master | Scrum Master, Team, Testing Team | Scrum Master, Product Owner, Project Manager | Project Manager, Product Owner, Business Owner | FirstAnswer
232 | The tool used to manage user stories is: | MSProject | Prompt | Rally | Quality Center | ThirdAnswer
233 | The role of the scrum master is to: | Assign work assignment to the team. | Remove impediments so the team can deliver sprint goals. | Assign story points to each story. | Update everyones capacity. | SecondAnswer
234 | The length of a sprint is: | 1 week | 2 weeks | 3 weeks | 4 weeks | SecondAnswer
235 | The purpose of poker planning is to: | Create user stories. | Estimate the effort by assigning story points. | Create tasks for user stories. | Assign resources to the tasks for the user stories. | SecondAnswer
236 | Team velocity represents: | The number of story points that can be completed in a sprint. | The number of stories that can be completed in a sprint. | The number of days the sprint will run for. | The teams available hours for the year. | FirstAnswer
237 | The sprint retrospective is held: | At the beginning of each sprint. | At the end of each month. | At the end of each sprint. | Quarterly. | ThirdAnswer
238 | SCRUM stands for: | Does not stand for anything. | Scheduled Collaborative Rally Updated Methodology | Scottish Club Rugby Union Methodology | Story Collective Reporting Under Master | FirstAnswer
239 | The backlog contains: | A prioritized list of user stories not assigned to a sprint. | A summary of completed user stories. | A list of storeis in random order that are assigned to a sprint. | A wish list of work that has not been funded yet. | FirstAnswer
240 | A story is considered finished when: | The 'to do' hours = 0. | The story is marked as Completed. | The story is marked as Accepted. | QA is finished testing. | ThirdAnswer
241 | When an obstacle stands in the way of completing a story task: | The tasked should be marked as 'Blocked 'in Rally. | The story should be assigned to the team blocking the task. | The story should be assigned to the scrum master. | The story and all its tasks should be moved to the backlog. | FirstAnswer
242 | The velocity report: | Points out key performers. | Is used to track the 'plan estimate' to the 'task estimate'. | Is used to compare teams to see who can get the most done. | Measures performance to the schedule. | FourthAnswer
243 | When there is no time left to complete a task in a story: | The resource needs to put in overtime to complete the task. | The task will not get done. | The task is moved to another sprint for completion. | The task is marked as 'Blocked' in Rally. | ThirdAnswer
244 | An agile project team has an impediment that they were unable to resolve amongst themselves due to lack of authority. This impediment is impeding the team from meeting their iteration goal. Which of the following action should the team take to resolve? | Raise the impediment at the Sprint Retrospective call | Raise the impediment with senior management quickly to resolve the issue | Raise the impediment again at the daily standup call with team members | Raise the impediment at the next sprint planning meeting and assign ownership | Raise the impediment with senior management quickly to resolve the issue
245 | What type of testing it is that ensures the product quality remains high throughout the development process? | Regression testing | Aggressive Automated testing | Ruthless automated Testing | Load testing | Ruthless automated Testing
246 | Why Agile is considered as "Value-Drive" approach? | Because Agile helps to deliver value in shorter duration | Because in Agile the order of work is determined by the value of the feature to the customer | Because Agile does not need planning it considers only value to customer | Because Agile helps to deliver the iterations quick | Because in Agile the order of work is determined by the value of the feature to the customer
247 | Which of the following best describes the technique that is used when there is a desire to make a collective decision among individuals, in a non-judgemental setting, to discuss a specific agenda item with the goal of coming up with a plan of action | Sprint planning meeting | Release planing meeting | Brainstorming | Business case review | Brainstorming
248 | Which of the following best describes tools product owners can use to better perform their role, enhance collaboraton in teams, and are especially effective when creating a product vision and the direction that hits the mark? | Innovation games | Vision setting | Project management practice | Emperical model | Innovation games
249 | Story maps are an effective technique to organize project features in which fashion? | Organize project features into user activities | Organize product features into a project roadmap | Organize product features into a single narrative mission statement | nize product features according to team preference | Organize project features into user activities
250 | During this meeting everyone provides a status update to the other team members. It is a 10 - 15 minute semi real time status meeting that allows participants to become aware of potential challenges as well as coordinate efforts to resolve issues? | Release planning meeting | Brevity meeting | Daily stand up meeting | Coolaboration meeting | Brevity meeting
251 | Identify which of the following is not a core element of the Scrum framework | Product owner | Sprint burndown | Sprint backlog | Release plan | Release plan
252 | Select the correct term from the following list refers to the ability to feel one's instinctive reaction to a situation, notice it, and consciously decide what to do with it? | Face reading | Rapid analisys | Empowerment | Emotional Intelligence | Emotional Intelligence
253 | Which is the technical Debt from the following options? | Growing defect backlog | Writing unit test | TDD | Automation script development | Growing defect backlog
254 | In Agile, the highest priority is to satisfy the customer through.... | collaboration. | face to face conversations. | early and continuous delivery of valuable software. | welcome changing requirements at anytime. | early and continuous delivery of valuable software.
255 | As per the agile manifesto, the art of maximizing the amount of work not done is essential is known as: | Great work | Responding to change | Simplicity | Complexity | Simplicity
256 | Businesspeople and developers must work together on what frequency? | Daily throughout the project. | weekly throughout the project. | Monthly throughout the project. | As and when required. | Daily throughout the project.
257 | Why welcome changing requirements, even late in development is important? | For customer's competitive advantage. | For customer satisfacation. | Does not matter. | For customer delight. | For customer's competitive advantage.
258 | What is deliverworking software frequency? | couple of weeks to a couple of months | couple of months to a couple of years | couple of days to a couple of weeks | couple of hours to a couple of days | couple of weeks to a couple of months
259 | What is agile manifesto's highest priority? | early and continuous delivery of valuable software | early and discrete delivery of valuable software | late and continuous delivery of valuable software | early and descrete delivery of valuable software | early and continuous delivery of valuable software
260 | What kind of individuals are required while building the products? | Energetic | Excited | Motivated | Enthusiastic | Motivated
261 | The most efficient and effective method of conveying information to and within a development team is: | face-to-face conversation. | Telephonic conversation. | Vedio conversation. | Live chat conversation. | face-to-face conversation.
262 | Which of the following would enhances agility? | technical excellence and good design | technical excellence only | good design only | Nothing would enhance the agility | technical excellence and good design
263 | Story point estimate is a measurement of _______ | Amount of effort involved in developing a feature | The complexity of developing it | The risk inherent in developing a feature | Do not know | Amount of effort involved in developing a feature
264 | The intersection of a trend line for work remaining (or backlog) and the horizontal axis indicating the most probable completion of work at the point in time would be found in which graphic representation? | Burn-down chart | Burn-up chart | Executive management report | Team velocity report | Burn-down chart
265 | Which of the following agile frameworks does not implement time-boxed iterations? | DSDM | FDD | Scrum | Lean | Lean
266 | Which of the following statement best describes "Governance" in an Agile environment? | Controlling the Agile teams | Agile project progress tracking | Making decisions in an uncertain environment | Directing the output of an Agile team | Making decisions in an uncertain environment
267 | What is being updated for a task in progress? | Effort consumed | Effort required | Some number | nothing should be updated | Effort required
268 | Which of the following is true concerning impediments? | A slow running server is not considered an impediment | It is the Product Owners job to remove impediments. | It is the Scrum Masters top priority to remove impediments | The Team should not use daily Scrum meetings to report impediments | It is the Scrum Masters top priority to remove impediments
269 | Who Is responsible for facilitating the Sprint Retrospective Meeting? | Team | Product Owner | Scrum Master | Project Manager | Scrum Master
270 | Which role is responsible for turning the Product Backlog into incremental pieces of functionality? | Everyone within the Project | Team | Scrum Master | Product Owner | Team
271 | Abnormal sprint terminations are extremely rare. In the unlikely event one is needed, who makes that decision? | Management | Team | Scrum Master | Product Owner | Product Owner
272 | Once team starts a Sprint, who determines how the Team does its work? | Project Manager | Scrum Master | Team | Team Lead | Team
273 | Which of the following statements is TRUE about Scrum teams and planning? | Scrum Teams place value in following a plan. But they value responding to change even more. | Traditional planning is replaced by the Sprint Burndown chart. | Scrum is intended to be an efficient way to carry out plans that have already been made. | Planning is not important in Scrum. | Scrum Teams place value in following a plan. But they value responding to change even more.
274 | What is the recommended duration of the Release Planning Meeting? | Four hours | 10% of the length of the Sprint | One day | Scrum does not define the length of Release Planning | Scrum does not define the length of Release Planning
275 | What is MOST likely to result if the Product Owner is not available during a Sprint? | The product increment may not meet expectations. | The Team extends the length of the Sprint until the Product Owner returns. | The Sprint is abnormally terminated. | The Scrum Master assumes the responsibilities of the Product Owner | The product increment may not meet expectations.
276 | What happens if, during a Sprint, the Product Owner identities a new, important Product Backlog item (PBI)? | The Scrum Master encourages the Team to include the extra item. | The Team works overtime to finish the PBI in the current Sprint | The Product Owner adds the new PBI to the Product Backlog | The Team extends the Sprint duration to include the new item. | The Product Owner adds the new PBI to the Product Backlog
277 | How do the principles behind the Agile Manifesto suggest approaching architecture? | Architecture emerges. | Architecture is defined and planned up front | Architecture is defined and implemented in the first iterations. | Architecture is not important but functionality is important | Architecture emerges.
278 | What is MOST important according to the Agile Manifesto? | Documentation and planning | People and how they communicate | Control and management | Processes and tools | People and how they communicate
279 | What is the role of Management in Scrum? | Management has no role in Scrum | To monitor development teams productivity | To identify and remove people that aren’t working hard enough. | continually monitor staffing levels of the Development Team. | Management has no role in Scrum
280 | According to Robert Greenleaf, Servant Leadership is best referred as | always striving to meet the highest priority needs of others. | Leading followers to achieve organizational objectives | All the above | None of these | always striving to meet the highest priority needs of others.
281 | Who is primarily responsible for Stakeholder & Customer value management? | Management | Team | Scrum Master | Product Owner | Product Owner
282 | By writing features to minimize the technical dependencies between them, the Product owner has the greatest amount of flexibility to _____ them | Develop | Assign | Prioritize | Defer | Prioritize
283 | Which of the following is not a core value of scrum | Commitment | Openness | Focus | Simplicity | Simplicity
284 | Which of the following patterns of spreading scrum is less aggressive, less risky, and used in less urgency situations. | Grow-and-split | Split-and-seed | Split into many | Grow to many | Grow-and-split
285 | Who is required to attend daily standup meetings | The development team and product owner | The development team | The Scrum team | The development team, scrum master and product owner | The development team
286 | Velocity is good and relevant input for | Iteration Planning | Release Planning | Burndown | velocity is not relevant to any planning | Release Planning
287 | When using Scrum, who is primarily responsible for making scope versus schedule trade-off decisions? | Project Manager | Team | Scrum Master | Product Owner | Product Owner
288 | When can a person released from project | Scrum Masters decision when to release him/her | Should wait until Sprint completed | Can be release at any point of the time of sprint, just make sure he/she gave proper KT | That is Project Managers responsibility | Should wait until Sprint completed
289 | As per Adkins Lyssa in "Coaching Agile Teams", what is the first step in building a high-performance Agile team? | Provide detailed requirements | Put the team under pressure | Set the expectations | Train the team with Agile practices | Set the expectations
290 | During a Daily Scrum meeting, Olivia mentions she has found some open source code she thinks will solve one of the problems she has been working on. She wants to implement it immediately. What is the best next step? | The Product Owner notes the impediment and solves the problem after the meeting | All members of the Team are told to evaluate Olivia s solution and report back to the team at the next Daily Scrum meeting. | After the Daily Scrum meeting is held. a separate meeting is conducted to discuss the open source solution. | The Scrum Master tells Olivia to prepare an example and presentation for the Team so they can consider using the code. | After the Daily Scrum meeting is held. a separate meeting is conducted to discuss the open source solution.
291 | A facilitator creates a "container", which provide the framework for the team to provide ____________? | Ideas and feedback | List of issues and respective options to solve them | List of Risks and respective work-arounds | Story points | Ideas and feedback
292 | What should be changing in a high performance company? | Leaders and management | Core values and purpose | Team members | Operating practices and business strategies | Operating practices and business strategies
293 | What are the desirable qualities of a Product Vision? | Features a detailed overview that enlightens and inspires | Outlines traceability back to overall corporate governance in IT investment | Describes why the project is pursued and the product desired end state | Provides a complete breakdown structure of the ROl formula | Describes why the project is pursued and the product desired end state
294 | Whet Is the approach that Scrum encourages when a Team determines It will be difficult to deliver any value by the end of a Sprint? | Immediately escalate to Senior Management | Extend the Sprint by a few days to accommodate the extra work. | Suggest the Product Owner abnormally terminate the Sprint | Together with the Product Owner. Focus on what can be done and identify a way to deliver something valuable at the end of each Sprint | Together with the Product Owner. Focus on what can be done and identify a way to deliver something valuable at the end of each Sprint
295 | When is the Sprint completed? | When tasks are completed | when committed items have met their definition of done | When the timebox expires | As determined by the size of the Team | When the timebox expires
296 | According to Scrum guidelines, who is responsible for hiring or assigning e new person into a Team? | The self-managing Team | Product Owner | This is outside of the scope of Scrum. | Scrum Master | This is outside of the scope of Scrum
297 | Which of the following is a characteristic of a good Team? | It seeks direction from the ScrumMaster | Its members all have similar level technical skills. | It is self-organizing | It waits for tasks to be assigned to it. | It is self-organizing
298 | Can the Product Owner and the ScrumMaster be the same person? | No. It would take too much of one person’s time | No. The person would have too much power and it would create confusion | Yes, as long as the person can balance both responsibilities with care | Yes. if the person has the authority and empowerment to do both things. | No. The person would have too much power and it would create confusion.
299 | Who can remove a team member from the team? | Scrum master | Product Owner | Project Manager | The Team | The Team
300 | Which of the flowing is primarily the Product Owners reasonability? | Determining the Teams daily scrum meeting time. | Determining the length of the Sprints. | Determining the appropriate technical solution for the project. | Determining the appropriate release date. | Determining the appropriate release date.
301 | Can a scrum master be part of development team? | Yes | No | Impossible | Not sure | Yes
302 | What is the role of Product Owner | Represents management to the project | Shields the team from external interferences | A change agent | Build and communicate Vision | Build and communicate Vision
303 | Which of the following prioritizes inputs into subsequent levels of product planning and is derived as an output od the product vision and roadmap? | Product backlogs | Product surveys | Input scenarios | Story boards | Product backlogs
304 | Which of the following is NOT a requirement of a mature product backlog? | All items in the product backlog are prioritized | All backlog items are estimated | All items in the product backlog are in user story format | All backlog items are more granular the closer in schedule they are to the iteration | All items in the product backlog are in user story format
305 | Scrum Master is a "Management" position. Is this true? | Some times based on the project type | Yes | No | Not sure | Yes
306 | Select the correct project environment to which Agile approach can be applied | Chaotic | Simple | Large size | Complex | Complex
307 | Which of the following is recomanded for Daily Scrum | Same place at the same time every work day | Place and time is not important | Regularly change the meeting place for a change | Its scrum master decision | Same place at the same time every work day
308 | Who are required for daily scrum meeting | Team | Team and Scrum Master | Team, Scrum Mater and Product Owner | Team, Scrum Mater, Product Owner and othe stack holders | Team
309 | Who can extend the sprint duration? | Scrum master | Product owner | Team | No one | No one
310 | Involving the team in planning and estimating and providing early feedback on Delivery Velocity is BEST used to mitigate what kind of risk? | Schedule Flaws | Requirements creep | Employee turnover | Poor productivity | Schedule Flaws
311 | When forming an Agile project team is BEST to use | Generalized Specialists | Top management officials | Highly specialized developers | All of the above | Generalized Specialists
312 | What is the unit of measurement that is used to measure the size of a user story for an Agile Project? | Function points | Story points | Work breakdown points | Velocity points | Story points
313 | How is Agile planning different from the traditional approach to planning? | Agile planning is done only once | Agile planning is non-iterative | Agile planning places emphasis on the plan | Agile planning places emphasis on planning and is iterative | Agile planning places emphasis on planning and is iterative
314 | The process of testing Delivered or "done done" stories is known as: | Unit Testing | Integration Testing | Exploratory Testing | Release Testing | Exploratory Testing
315 | Which of the following is NOT one of the five core risk areas common to all projects? | Specification Breakdown | Scope Creep | Strategic Alienation | Intrinsic Schedule Flaw | Strategic Alienation
316 | A persona used within an Agile user story can be thought of as: | A person who will only use the application in frequently | A person who will influence early adopters of the application | A formally-assigned user-acceptance tester | An imaginary representation of a user role | An imaginary representation of a user role
317 | When analyzing processes, what becomes increasingly significant for managers to understand in regards to individual skills? | A group understanding of processes allows teams to executive their jobs more effectively and efficiently, but it can never substitute skill | A process is more easily developed when the customer is more directly involved in its development | Skilled individuals are not necessarily required to be involved with analyzing processes | Skill sets are absolutely crucial in the planning and execution of specific processes, but not its analysis | A group understanding of processes allows teams to executive their jobs more effectively and efficiently, but it can never substitute skill
318 | Which chart helps an Agile practitioner understand scope changes over iterations? | Release burndown bar chart | Release burndown graph | Prioritized product backlog | Release burn up chart | Release burndown bar chart
319 | Which of the following is a correct statement from agile manifesto? | Following a Plan instead of Responding to Change | Working Software instead of Comprehensive Documentation | Customer Collaboration over Contract Negotiation | Tools and Processes instead of Individuals & Interactions | Customer Collaboration over Contract Negotiation
320 | What is important and necessary to start a Sprint using Scrum? | Release plan and budget | Sponser and funds | Vision and Product Backlog | Scrum team | Vision and Product Backlog
321 | If the bottom of the release burndown chart stays below horizontal axis, what does it indicate? | Total work in the project is more than initially planned | Some features are removed from the scope | It does not indicate any specific scenario | Total work in the project is less than initially planned | Total work in the project is more than initially planned
322 | According to the Scrum method, who all participates in the decision of how to achieve the Sprint goal? | Senior management and product owner | Team with Subject Matter Experts | The scrumm team | The development team | The scrumm team
323 | How is the scope creap best managed in an Agile project? | By managing the product backlog effectively | By pushing the changes to the next release planning meeting | By cancelling the current iteration and start a new iteration | By accommodating the changes to the product backlog per customer requirements but keeping the iteration plan steady | By accommodating the changes to the product backlog per customer requirements but keeping the iteration plan steady
324 | Which of the following will least help team in becoming solid co-operator and collaborator? | Develop team members technical skills | Team member takes responsibility of his or her actions rather than blaming and denying | Team members get rid of their vanity during work. | Develop curiosity in team members | Develop team members technical skills
325 | You are piloting the agile process first time in your organization, and you are observing that your management is trying to micro manage the project because they are worried about the project execution progress, what should you do? | Tell the manager that in agile they have no role to play | Decide to abandon the pilot and get back to the old way of doing things | Introduce the management about the agile processes / practices and introduce them to visual controls, help them understanding the visual controls | Let management get involve in project and let them micro manage the project, after all he is also responsible for the delivery. | Introduce the management about the agile processes / practices and introduce them to visual controls, help them understanding the visual controls
326 | What do you understand by business-value “points”? | It is a estimate of relative business value of each feature | It represents relative size of the feature | It captures the teams preference of ordering feature for development | It represents cost associated with implementation of feature | It is a estimate of relative business value of each feature
327 | Which of the following is not expected from the project Sponsor? | Articulation of Product Vision | Be present and attentive in sprint review | Talk about business trade-offs and managing expectations | Review of sprint backlog | Review of sprint backlog
328 | Which of the following is not a responsibility of product owner? | Business value driver | Vision keeper | Task allocator | One ultimately responsible | Task allocator
329 | Which of the following is not expected to be achieved by daily stand-up meeting? | Peer Pressure | Daily Commitment | Finding solutions of impediments | Fine grain coordination | Finding solutions of impediments
330 | The acronym DEEP represent four quality of well groomed product backlog, what does E and E stands for? | Estimated and Easy | Economical and Easy | Estimated and Emergent | Economical and Emergent | Estimated and Emergent
331 | CRACK, an effective product owner is Committed , Responsible , Authorized , collaborative and........ | Kean | Knowledgeable | Kind | Keeper of agile practice | Knowledgeable
332 | You are the agile coach , and during the sprint you observed that team is making wrong design decision for one story , you raised some queries to provoke discussions which has potential to show the design flaws but team didn't get it. What should you do? | Call a special meeting and demonstrate flaws in the design | Talk to Product owner and explain that this can potentially lead to poor quality product | Do nothing about it, let the team take the decision and fail | Discuss this issue in Stand-up meeting | Do nothing about it, let the team take the decision and fail
333 | Which of the following meeting closely aligns the agile principle of satisfying the customer through early and continuous delivery of valuable software? | Sprint retrospective | Sprint planning | Daily scrum | Sprint review | Sprint review
334 | One of the team’s velocities are 30,29,32 story points for the last 3 consecutive sprints. What would be the team’s velocity for the next sprint based on the yesterday’s weather? | 30 | 31 | 29 | 34 | 34